## Рус за 2017 год
In accordance with paragraph 7-5 of Article 7 of the Law of the Republic of Kazakhstan dated 09.07.1998 No. 272-I "On Natural Monopolies"
Information
of the natural monopoly subject
on the implementation of the investment program (project) of
JSC "MRPGC"
providing services for the transmission and distribution of electricity
for 2017
№ п/п | Information on planned and actual volumes of provision of regulated services (goods, works) | [5 empty] | Profit and loss statement, thous. KZT | The amount of the investment program (project) |  |  |  | Information on actual conditions and amounts of financing of the investment program (project), thous. Tenge |  |  |  | Information on the comparison of the actual performance indicators of the investment program (project) with the indicators approved in the investment program (project) * | [7 empty] | Explanation of the reasons for the deviation of the achieved actual indicators from the indicators in the approved investment program (project) * | Evaluation of improving the quality and reliability of the regulated services provided (goods, works) * | Отклонение | Причины отклонения
| Name of regulated services (goods, works) and serviced territory | Name of events | Unit of measurement | Quantity in physical terms |  | Period of service provision within the investment program (project) |  | Plan | Fact | deviation | reasons for deviation | Own funds (depreciation allocations) | Own funds (profit) | borrowed funds | Budgetary funds | Improvement of performance indicators,%, by implementation year, depending on the approved investment program (project) |  | Decrease in depreciation of (physical) fixed assets (assets),%, by years of implementation, depending on the approved investment program |  | Reduction of losses,%, by years of implementation, depending on the approved investment program (project) |  | Reduction of accidents, by years of implementation, depending on the approved investment program (project)
|  |  |  | plan | fact | [10 empty] | last year fact | fact of the current year | last year fact | fact of the current year | plan | fact | last year fact | fact of the current year
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
2 | services for the transmission and distribution of electricity in the territory of Mangystau region | Construction of power transmission line-220kV Aktau-Karazhanbas with autotransformer 1x125MVA at Node Distribution Substation "Karazhanbas" | km/pcs. | 198,6/1 | 147/1 | 2013-207 | 2640817 | 1325688.7518 | 2405678.3824 | 1079989.6306 | The increase in the approved amount of the project was within the framework of the project adjustment, which provided for an increase in transformer capacity from 125 MVA to 150 MVA, replacement of existing 16 MVA transformers with 25 MVA, replacement of morally and physically obsolete current transformers and voltage transformers, and also considered the suppression of VL-220kV with communications not foreseen by the project. The adjustment of the project received a positive opinion from the Republican State Enterprise of State Expertise No. 01-0553 / 15 dated 12/21/2015. Also in 2017, in the course of work on the expansion of the open switchgear-220kV Thermal Power Plant-3 "MANGISTAU NUCLEAR ENERGY COMBINAT-Kazatomprom" LLP additionally demanded to provide for the improvement of the territory and outfit trail attire, on the upper edge of the fence, a visor from the wire "Egoza" , antidopic barrier. Also for the expansion of an open switchgear-220kV, the project did not provide for the installation of an oil pan, the installation of cable trays, and filling the site with rubble. The completion is planned for 2018. | 611792.6829 | 1625051.8583 | 168833.8412 |  | - | - | - | - | - | - | - | - | - | - | #REF! | Long-term project. The increase in the approved project amount was part of the project adjustment, where it was planned to increase the transformer capacity from 125 MVA to 150 MVA, replace the existing 16 MVA transformers with 25 MVA, replace morally and physically outdated current transformers and voltage transformers, and consider crossing the 220 kV overhead line with communications not foreseen by the project. project adjustment received a positive opinion of the RSE State Expertise No. 01-0553 / 15 dated 21.12.2015 | 98.8161
3 |  | Modernization (reconstruction) of equipment Open switchgear-35kV at 110/35 / 6kV substation "Plateau", substation 110/35 / 6kV "Vadina" | piece / off | 2./10 | 2./10 | 2015-2017 |  | 8330 | 11050.0298 | 2720.0298 | Construction, installation and commissioning work has been completed. New equipment commissioned. | 8330 | 2720.0298 |  |  | - | - | - | - | - | - | - | - | - | - | #REF! | The project is completed, the object was put into operation. | 2720.0298
4 |  | Reconstruction of equipment Open switchgear -35kV, 110kV with replacement — separator — 110kV short circuiter and 35kV reclosers installed at 110/35 / 6kV substation “East Zhetybai” | piece / off | 1./9 | 1./9 | 2015-2017 |  | 4900 | 4900 | 0 | Construction, installation and commissioning work has been completed. New equipment commissioned. | 4900 |  |  |  | - | - | - | - | - | - | - | - | - | - | #REF! | In 2016, 18 692 units of metering devices were installed. The project has been completed and the facility has been put into operation.
5 |  | Modernization of a 6kV switchgear at a 110 / 6kV "steam treatment" substation with the replacement of a closed switchgear-6kV with a package outdoor switchgear of 6kV | pcs./cell | 1./25 | 1./25 | 2015-2017 |  | 74017.177 | 74490.742 | 473.565 | Construction, installation and commissioning work has been completed. New equipment commissioned. | 19276.687 | 473.565 | 54740.49 |  | - | - | - | - | - | - | - | - | - | - | #REF! | The project is rolling over to 2017.Deviation from the approved plan, in connection with the re-examination of the state. | 473.565
6 |  | Construction of electric power line 110 kV from substation Uzen -220 kV to substation 110/35 / 6kV Plateau length (1х18.7 km) with replacement of 1х40MVA transformer | km/pcs. | 1х18,7 | 1 | 2015-2018 |  | 523513.8589 | 463144.5818 | -60369.2771 | Construction and installation work is underway to implement this project. Completion is scheduled for 2018. |  | 311044.5818 | 152100 |  | - | - | - | - | - | - | - | - | - | - | #REF! | The project is moving to 2017. Deviation from the approved plan, due to technological difficulties in the manufacture of the package outdoor switchgear equipment.
7 |  | Modernization (reconstruction) of the equipment of outdoor switch-gear -110kV to substation 220/110 / 10kV "Uzen" No. of cells 1,2,7,8,11,12,15,16,24,25,26,27,28,29, 30,31,32 | . | 17 | 7 | 2015-2018 |  | 200846.3469 | 262664.2129 | 61817.866 | Currently, the Design and Budget Documentation has been completed with an estimated cost of more than pledged.90 Obtained the opinion of the Republican State Enterprise of State Expertise No. 15-0093 / 16 dated 11.04.2016. This project is planned to be completed in 2018. |  | 262664.2129 |  |  | - | - | - | - | - | - | - | - | - | - | #REF! | The project is completed, the object was put into operation.
8 |  | Modernization (reconstruction) of equipment Open switchgear-110 substation 110/35 / 6kV "Gorodskaya" | piece / off | 1./2 | 1./2 | 2015-2018 |  | 44311.1005 | 50116.9791 | 5805.8786 | Construction, installation and commissioning work has been completed. New equipment commissioned. | 48499.939 | 1617.0401 |  |  | - | - | - | - | - | - | - | - | - | - | #REF! | The project is completed, the object was put into operation. | 1617.0401
9 |  | Modernization (reconstruction) of equipment Open switchgear-110kV PS 110 / 6-6kV "Industrial Zone" | piece / off | 1./2 | 1./2 | 2015-2018 |  | 32224.0285 | 36564.056 | 4340.0275 | Construction, installation and commissioning work has been completed. New equipment commissioned. | 36564.056 |  |  |  | - | - | - | - | - | - | - | - | - | - | #REF!
10 |  | Modernization (reconstruction) of equipment 6kV closed switchgear substation 35 / 6kV "drilling mud plant" and substation-35 / 6kV "Vostochnaya" | piece / off | 2./41 | 2./41 | 2016-2017 |  | 513020.138 | 522389.79 | 9369.652 | Construction, installation and commissioning work has been completed. New equipment commissioned. | 239318.9664 | 11029.5219 | 272041.3018 |  | - | - | - | - | - | - | - | - | - | - | #REF! | В 2016 году разработка ТЭО завершена. | 11029.5219
11 |  | Modernization (reconstruction) of the equipment of the 6 kV indoor switchgear of the 110/6 kV Karamandybas substation, 110/6 kV thermal station and the upgrade | pcs./cell | 2./39 | 2./39 | 2016-2017 |  | 499686.841 | 527433.8143 | 27746.9733 | Construction, installation and commissioning work has been completed. New equipment commissioned. | 277468.3759 | 29380.0572 | 220585.3813 |  | - | - | - | - | - | - | - | - | - | - | #REF! | В 2016 году разработка ТЭО завершена. | 29380.0572
12 |  | Replacement of power transformers at 110/35 / 6kV "Zhetybay" substation with a capacity of 2x40MVA and 2x63MVA | pieces | 2 | - | 2015-2017 |  | 32967.492 | 0 | -32967.492 | The development of design and estimate documentation was canceled due to the absence of the need to replace transformers, since there is no increase in additional loads by analyzing the code for issuing technical conditions and developing the infrastructure of Zhetybai in general |  |  |  |  | - | - | - | - | - | - | - | - | - | - | #REF! | Реализация проекта завершена, объект введен в эксплуатацию.
13 |  | Replacement of power transformers at the 35 / 6kV substation "Block-type pumping station-3" with a capacity of 2x6.3MVA and 2x10MVA | pieces | 2 | 2 | 2015-2017 |  | 177556.663 | 179127.466 | 1570.803 | Construction, installation and commissioning work has been completed. New equipment commissioned. | 29546.6409 | 1570.803 | 148010.0221 |  | - | - | - | - | - | - | - | - | - | - | #REF! |  | 1570.803
14 |  | Replacement of power transformers at 35 / 6kV "Block-type pumping station-2" 9 substation (Block-type pumping station) with a capacity of 2x6.3MVA and 2x10MVA | pieces | 2 | 2 | 2015-2017 |  | 177556.663 | 179127.466 | 1570.803 | Construction, installation and commissioning work has been completed. New equipment commissioned. | 29546.6409 | 1570.803 | 148010.0221 |  | - | - | - | - | - | - | - | - | - | - | #REF! | Проект переходящий на 2017 год. Отклонение от утвержденного плана, в связи с поздним сроком заключения договора.
15 |  | Modernization (reconstruction) of the equipment of outdoor switchgear-35kV substation 35 / 6kV "Block-type pumping station-2,3,4,5", Tasbulat, Beket-Ata, Akkudyk, Akzhigit | piece / off | 7./22 | 7./22 | 2015-2018 |  | 549208.84 | 567654.4193 | 18445.5793 | Construction, installation and commissioning work has been completed. New equipment commissioned. |  | 231975.4777 | 335678.9416 |  | - | - | - | - | - | - | - | - | - | - | #REF! | Проект переходящий на 2017 год. Модернизация оборудования ОРУ-35кВ завершена.
16 |  | Modernization (reconstruction) of equipment Open switchgear-35kV and ZRU-6kV substation 35 / 6kV "cold filter plugging point" | piece / off | 1./17 | - | 2017-2018 |  | 24703.0214 | 23178.5714 | -1524.45 | Design estimates developed, agreed with the JSC "MRPGC" Construction and installation work is planned for 2018. | 23178.5714 |  |  |  | - | - | - | - | - | - | - | - | - | - | #REF!
17 |  | Modernization (reconstruction) of outdoor switch-gear 35 kV and Package outdoor switchgear 6.10 kV at substation 35 \ 10 kV Tigen, Zharmysh, Kyzyl-Turan, Ushtagan, Shaiyr, Kyzan, Tushchykuduk, Karyernaya (Beyneu) | pcs./cell | 9./12 | 9./12 | 2015-2018 |  | 11000 | 77300 | 66300 | Development Design and estimate documentation is completed. | 77300 |  |  |  | - | - | - | - | - | - | - | - | - | - | #REF! | Проект переходящий на 2017 год. Отклонение от утвержденного плана, в связи с поздним сроком заключения договора
18 |  | Acquisition of fixed assets and intangible assets | [5 empty] | 87677.078 | 302719.2702 | 215042.1922 | Due to production needs, power and current transformers, instruments and equipment, as well as technological vehicles were purchased | 302719.2702 |  |  |  | - | - | - | - | - | - | - | - | - | - | #REF!
19 |  | Development of design and estimate documentation for the project "Modernization of equipment for 35 kV outdoor switchgear of 4 cells at -110 / 35 / 6kV Zhetybai substation | [6 empty] | 4100 | 4100 |  | 4100 |  |  |  | - | - | - | - | - | - | - | - | - | - | #REF!
20 |  | Modernization (reconstruction) of equipment of outdoor switch-gear -35kV substation 35 / 6kV "Sauskan" | [6 empty] | 4100 | 4100 |  | 4100 |  |  |  | - | - | - | - | - | - | - | - | - | - | #REF!
|  | TOTAL | [5 empty] | 4287208 | 5695739.7813 | 1408531.7813 |  | 1716641.8307 | 2479097.9506 | 1500000 |  | - | - | - | - | - | - | - | - | - | - | #REF!
| * - when approving the investment program of JSC "MRPGC" for 2016-2020, the performance indicators of the investment program were not approved | [9 empty] | depreciation
[11 empty] | % | 1392841.9751
|  | Председатель Правления | [9 empty] | С. Игисинова

## Рус за 1 полугодие 2015 год (hidden)
В соответствии с пунктом 7-6 статьи 7 Закона РК от 09.07.1998 года № 272-I "О естественных монополиях и регулируемых рынках"
Информация
субъекта естественной монополии
об исполнении инвестиционной программы (проекта)
АО "МРЭК"
оказывающего услуги по передаче и распределению электроэнергии
за 1 полугодие 2015 года
№ п/п | Наименование показателей инвестиционной программы (проекта) | Кем утверждена (дата, номер приказа) | Годы реализации мероприятий | Сумма инвест. программы, тыс. тенге | Отчет о прибылях и убытках, тыс. тенге* | Информация о плановых и фактических объемах предоставляемых регулируемых услуг (товаров, работ), тыс.кВтч. |  | Источник инвестиций (фактические условие) | Исполнение, фактические параметры (показатели) мероприятия, объекта инвестиционной программы, учтенной в тарифе (ежеквартально, с нарастающим итогом)** |  |  |  |  | Отклонение | Причины отклонения
[6 empty] | План | Факт |  | Количество в натуральном показателе | Сумма инвестиций | источник инвестиций
[11 empty] | Собственные средства (амортизационные отчисления) | Собственные средства (прибыль) | заемные средства (выпуск облигаций)
1 | Крупные стратегические проекты |  |  | 3037386 | 862147 | 1279800 | 1279551 |  |  | 1136311.6843 | 1044931.188 | 91380.4963 | 0 | -1901074.3157
1.1 | Строительство ЛЭП-220кВ Актау-Каражанбас с автотрансформатором 1х125МВА на УРПС "Каражанбас" | Совместный приказ Департамента Комитета по регулированию естественных монополий и защите конкуренции Министерства национальной экономики РК по Мангистауской области от 03 декабря 2014 года №12-ОД и Министерства энергетики РК от 31 декабря 2014 года №244 | 2013-2016 | 896659 |  |  |  | Собственные средства | 1 | 2650 | 2650 |  |  | -894009 | Переходящий проект. Договор заключен. Проект на стадии реализации
1.2. | Строительство ЛЭП-220кВ Актау-Узень с автотрансформаторами 1х250МВА на нефтепромыслах месторождения "Узень" |  | 2014-2015, 2019-2020 | 610700 | [9 empty] | -610700 | Переходящий проект. Договор заключен. Проект на стадии реализации
1.3. | Строительство регионального-диспетчерского центра |  | 2013-2016 | 542027 |  |  |  |  | 1 | 460563.1103 | 460563.1103 |  |  | -81463.8897 | Переходящий проект. Договор заключен. Проект на стадии реализации
1.4. | Реализация проекта по АСКУЭ в сетях 6-10/0,4кВ АО "МРЭК" с внедрением телемеханики и телеизмерений |  | 2013-2016 | 988000 |  |  |  |  | 1 | 653888.3611 | 581718.0777 | 72170.2833 |  | -334111.6389 | Переходящий проект. Договор заключен. Проект на стадии реализации
1.5. | Реконструкция ПС 110/10 кВ "Акшукур" |  | 2013-2015 | [5 empty] | 1 | 19210.2129 |  | 19210.2129 |  | 19210.2129 | Выполнены пусконаладочные работы, авторский и технический надзор
2 | Расширение, модернизация и развитие |  |  | 2241771 | [5 empty] | 45315.727 | 0 | 45315.727 | 0 | -2196455.273
2.1. | Реконструкция ПС ПТФ с переводом напряжения 110кВ и заменой силовых трансформаторов |  | 2015-2018 | 856245 |  |  |  | Собственные средства | [5 empty] | -856245
2.2. | Реконструкция ПС-110/6 кВ ПТБ |  | 2014-2016 | 821100 | [9 empty] | -821100
2.3. | Обслуживание ВЛ-110кВ, ВЛ-220кВ с целью прогнозирования срока службы и повышения грозоупорности ВЛ |  | 2014-2015 | 12326 | [9 empty] | -12326 | Переходящий проект. Договор заключен. Проект на стадии реализации
2.4. | Замена ОД/КЗ-110 кВ на элегазовые выключатели на ПС 110/6 кВ Каражанбас-2 |  | 2013-2015 | [5 empty] | 1 | 728.725 |  | 728.725 |  | 728.725 | Завершение проекта, который был приостановлен актом о приостановке выполнения работ в 2014 году
2.5. | Замена ОД/КЗ-110 кВ на элегазовые выключатели на ПС 110/6 кВ ПТВ |  | 2013-2015 | [5 empty] | 2 | 23485.8868 |  | 23485.8868 |  | 23485.8868 | Завершение проекта, который был приостановлен актом о приостановке выполнения работ в 2014 году
2.6. | Замена ОД/КЗ-110 кВ на элегазовые выключатели на ПС 110/35/10 кВ Форт |  | 2013-2015 | [5 empty] | 2 | 10275.2541 |  | 10275.2541 |  | 10275.2541 | Завершение проекта, который был приостановлен актом о приостановке выполнения работ в 2014 году
2.7. | Замена ОД/КЗ-35кВ на элегазовые выключатели на ПС 35/6 кВ Карьерная |  | 2013-2015 | [5 empty] | 2 | 5234.8611 |  | 5234.8611 |  | 5234.8611 | Завершение проекта, который был приостановлен актом о приостановке выполнения работ в 2014 году
2.8. | Модернизация ячеек КРУН-6 кВ на РП Жетыбай |  | 2014-2015 | 52100 | [9 empty] | -52100 | Планируется объявление тендера
2.9. | Установка SCADA в распределительных сетях с заменой трансформаторов и провода |  | 2013 | 500000 | [9 empty] | -500000
2.10. | Услуги по разработке проекта "Водоснабжение питьевой водой ремонтно-производственной базы" |  | 2014-2015 |  |  |  |  | Собственные средства | 1 | 5591 |  | 5591 |  | 5591 | В связи с необходимостью осуществления водоснабжения объектов АО «МРЭК» в 2014 году были выполнены проектно-изыскательные работы по монтажу системы городского водопровода до РПБ АО «МРЭК». Однако на основании дополнительного соглашения , в связи с длительным сроком получения разрешения от владельцев подземных коммуникаций на производство работ, действие договора было продлено до 31 января 2015 года
3 | Техническое перевооружение |  |  | 0 | [5 empty] | 842.622 | 0 | 842.622 | 0 | 842.622
3.1. | Программное обеспечение |  | 2015 |  |  |  |  | Собственные средства |  | 842.622 |  | 842.622 |  | 842.622 | Приобретены лицензии на обновление программных продуктов
| ИТОГО |  |  | 5279157 | [5 empty] | 1182470.0332 | 1044931.188 | 137538.8452 | 0 | -4096686.9668
|  |  |  | 5279157 | [5 empty] | 1182470.0332 | 1044931.188 | 137538.8452 | 0 | -4096686.9668
-4184686.9668