## Рус за 2015 год
In accordance with paragraph 7-5 of article 7 of the Legislation of the Republic of Kazakhstan dated 09.07.1998 № 272-I "On natural monopolies "
Information
natural monopoly entity
about execution of the investment program (project)
JSC "MPDC"
providing services for the transmission and distribution of electricity
for 2016
item number | Information on planned and actual volumes of regulated services (goods, works) | [5 empty] | Profit and loss statement, thousand KZT* | The amount of the investment program (project) |  |  |  | Information on the actual conditions and amounts of financing of the investment program (project), thousand tenge |  |  |  | Information on comparison of actual performance indicators of the investment program (project) with the indicators approved in the investment program (project)* | [7 empty] | Explanation of the reasons for the deviation of the achieved actual indicators from the indicators in the approved investment program (project)* | Assessment of improving the quality and reliability of regulated services (goods, works) * | Отклонение | Причины отклонения
| Name of regulated services (goods, works) and served area | The name of the events | Unit of measure | The quantity in physical indicators |  | Period of service provision within the investment program (project) |  | Plan | Fact | Deviation | Reasons for deviation | Equity (depreciation deductiables) | Own funds (profit) | Borrowed funds | Budgetary funds | Improvement of production indicators, %, by year of implementation depending on the approved investment program (project) |  | Lowering the depreciation (physical) of fixed assets (assets), %, by years of implementation, depending on the approved investment program. |  | Reduction of losses, %, by years of implementation depending on the approved investment program (project) |  | Reduction of accidents by year of implementation depending on the approved investment program
|  |  |  | plan | fact | [10 empty] | fact of previous year | the fact of the current year | fact of previous year | the fact of the current year | plan | fact | fact of previous year | the fact of the current year
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
2 | power transmission and distribution services in the Mangystau region | Construction of transmission line-220kV Aktau-Karazhanbas with autotransformer 1x125MBA on management of construction projects "Karazhanbas" | km/PCs. | 198,6/1 | - | 2013-2016 | 1840895 | 6020895 | 6546788.1541 | 525893.1541 | Long term project. The increase in the approved amount of the project was within the framework of the project adjustment, which provided for an increase in transformer capacity from 125 MVA to 150 MVA, replacement of existing 16 MVA transformers with 25 MVA, replacement of morally and physically obsolete current transformers and voltage transformers, and the intersection of VL-220 kV with communications not foreseen by the project was also considered. correction of the project received a positive conclusion RSE state expertise №01-0553/15 from 21.12.2015 year | 514147.0604 | 369332.4422 | 5663308.6515 |  | - | - | - | - | - | - | - | - | - | - | #REF! | Долгосрочный проект. Увеличение утвержденной суммы проекта было в рамках корректировки проекта, где было предусмотрено увеличение трансформаторной мощности с 125 МВА до 150 МВА, замена существующих трансформаторов 16 МВА на 25 МВА, замена морально и физически устаревших трансформаторов тока и трансформаторов напряжения, также было рассмотрено пересечение ВЛ-220кВ с коммуникациями непредусмотренные проектом. корректировка проекта получила положительное заключение РГП Госэкспертиза №01-0553/15 от 21.12.2015 года
3 |  | Construction of regional dispatch center | PCs. | 1 | 1 | 2013-2016 |  | 642630.6526 | 688865.0329 | 46234.3803 | The project has been completed and the facility has been put into operation. | 688865.0329 |  |  |  | - | - | - | - | - | - | - | - | - | - | #REF! | Реализация проекта завершена, объект введен в эксплуатацию.
4 |  | Implementation of the project pertatining to the automatic system for commercial accounting of power consumption in 6-10/0.4 kV networks of JSC "MPDC" with the introduction of telemechanics and telemetry | PCs/users | 1/19000 | 1/18692 | 2013-2016 |  | 212428.0198 | 226251.3541 | 13823.3343 | In 2016, 18 692 units of metering devices were installed. The project has been completed and the facility has been put into operation. | 226251.3541 |  |  |  | - | - | - | - | - | - | - | - | - | - | #REF! | В 2016 году смонтировано 18 692 шт. приборов учета. Реализация проекта завершена, объект введен в эксплуатаци.
5 |  | The construction of transmission lines 110 kV from substation "Uzen"-220kV to substation 110/35/6kV Plateau length (1х18,7 km) with the replacement of transformer 1х40МВА | km/PCs. | 1x18,7 | - | 2015-2018 |  | 9120 | 1349.985 | -7770.015 | The project is rolled over to 2017. Deviation from the approved plan, in connection with the re-examination of the state. | 1349.985 |  |  |  | - | - | - | - | - | - | - | - | - | - | #REF! | Проект переходящий на 2017 год.Отклонение от утвержденного плана, в связи с перепрохождением госэкспертизы.
6 |  | Modernization of the RU-6 kV at the substation 110/6kV "PTV" with the replacement of indoor switchgear-6 kV for switchgear-6kV | PCs/cells | 1./25 | - | 2015-2016 |  | 242361 | 168238.1444 | -74122.8556 | The project is rolling over to 2017. Deviation from the approved plan, due to technological difficulties in the manufacture of equipment outdoor metal-clad switchgear. |  | 168238.1444 |  |  | - | - | - | - | - | - | - | - | - | - | #REF! | Проект переходящий на 2017 год. Отклонение от утвержденного плана, в связи с технологическими сложностями при изготовлении оборудования КРУН.
7 |  | Reconstruction of outdoor switchgear 35 kV,110 kV with the replacement of the OD/short circuit-110 kV and 35 kV installation of reclosers at the substation 110/35/6kV "East Zhetybay" | PCs/off | 1./9 | 1./7 | 2015-2016 |  | 254563 | 254399.53 | -163.47 | The project has been completed and the facility has been put into operation. |  | 72052.1696 | 182347.3604 |  | - | - | - | - | - | - | - | - | - | - | #REF! | Реализация проекта завершена, объект введен в эксплуатацию.
8 |  | Modernization (reconstruction) of outdoor switchgear 35 kV at substation 110/35/6 " substation "Dent" and substation "Plateau" | PCs/off | 2./10 | 2./15 | 2015-2016 |  | 512514.4359 | 512230.531 | -283.9049 | The project has been completed and the facility has been put into operation. |  | 146104.5428 | 366125.9881 |  | - | - | - | - | - | - | - | - | - | - | #REF! | Реализация проекта завершена, объект введен в эксплуатацию.
9 |  | Reconstruction of distribution networks with replacement of packaged transformer substation | km/PCs. | 601/300 | - | 2015-2019 |  | 3780 | 3780 | 0 |  | 3780 |  |  |  | - | - | - | - | - | - | - | - | - | - | #REF!
10 |  | Feasibility study for the installation of ground wire with the VOLS on VL-110 kV 220 kV of JSC "MPDC" | PCs. | 1 | 1 | 2014-2016 |  | 3313.937 | 2985.7143 | -328.2227 | In 2016, the feasibility study was completed. | 2985.7143 |  |  |  | - | - | - | - | - | - | - | - | - | - | #REF! | В 2016 году разработка ТЭО завершена.
11 |  | Feasibility study for gas supply to the base of JSC "MPDC in order to reduce electricity consumption for own needs in the framework of the program of energy saving and energy efficiency | PCs. | 1 | 1 | 2015-2016 |  | 1235.6937 | 1235.6937 | 0 | In 2016, the feasibility study was completed. | 1235.6937 |  |  |  | - | - | - | - | - | - | - | - | - | - | #REF! | В 2016 году разработка ТЭО завершена.
12 |  | Replace OD/short circuit-110 kV gas-insulated circuit breakers at the substation 110/6 kV Karazhanbas-2 |  |  |  | 2013-2016 |  | 5945 | 5216.2884 | -728.7116 | The project has been completed and the facility has been put into operation. | 5216.2884 |  |  |  | - | - | - | - | - | - | - | - | - | - | #REF! | Реализация проекта завершена, объект введен в эксплуатацию.
13 |  | The replacement of power transformers at the substation 35/6kV "MGPS-3" with a capacity of 2x6,3МВА on 2х10МВА | PCs. | 2 | - | 2015-2018 |  | 1330 | 1330 | 0 |  | 1330 |  |  |  | - | - | - | - | - | - | - | - | - | - | #REF!
14 | power transmission and distribution services in the Mangystau region | Equipment modernization (reconstruction) of the cells of 110 kV outdoor switchgear at the substation 220/110/10kV "Uzen" No. 1,2,7,8,11,12,15,16,24,25,26,27,28,29,30,31,32 | pris. | 17 | - | 2015-2019 |  | 214685.4657 | 112207.012 | -102478.4537 | The project is rolled over to 2017. Deviation from the approved plan, due to the late date of the contract. |  | 112207.012 |  |  | - | - | - | - | - | - | - | - | - | - | #REF! | Проект переходящий на 2017 год. Отклонение от утвержденного плана, в связи с поздним сроком заключения договора.
15 |  | Modernization (reconstruction) of outdoor switchgear 35, 110 and the RU-6 kV of substation 110/35/6 "Urban" | PCs/off | 1./7 | 1./7 | 2015-2018 |  | 335725.223 | 306018.5 | -29706.723 | The project is rolling over to 2017. Modernization of the equipment of the outdoor switchgear -35kV is completed. |  | 117800.5 | 188218 |  | - | - | - | - | - | - | - | - | - | - | #REF! | Проект переходящий на 2017 год. Модернизация оборудования ОРУ-35кВ завершена.
16 |  | Modernization (reconstruction), equipment of indoor switchgear-6 kV substation of 110/6kV "Karamandybas", substation 110/6kV "Thermal" and modernization of relay protection and automation substation | PCs/cells | 2./39 | - | 2015-2017 |  | 2520 | 2520 | 0 |  | 2520 |  |  |  | - | - | - | - | - | - | - | - | - | - | #REF!
17 |  | Equipment modernization (reconstruction) of 110 kV outdoor switchgear and indoor switchgear-6kV S 110/6-6 kV "Industrial zone" | PCs/off | 1./2 | - | 2015-2018 |  | 65238 | 43485.661 | -21752.339 | The project is rolled over to 2017. Deviation from the approved plan, due to the late date of the contract. |  | 43485.661 |  |  | - | - | - | - | - | - | - | - | - | - | #REF! | Проект переходящий на 2017 год. Отклонение от утвержденного плана, в связи с поздним сроком заключения договора
18 |  | Modernization (reconstruction) of outdoor switchgear 35 kV and indoor switchgear-6 kV of substation 35/6kV "Glinzavod" and 35/6kV substation "Vostochnaya" | PCs/off | 2./41 | - | 2015-2017 |  | 2520 | 2520 | 0 |  | 2520 |  |  |  | - | - | - | - | - | - | - | - | - | - | #REF!
19 |  | Equipment modernization (reconstruction) of outdoor switchgear 35 kV at substation 35/6kV "Sauskan" | PCs/off | 1./2 | - | 2015-2018 |  | 1025.5 | 1025.5 | 0 |  | 1025.5 |  |  |  | - | - | - | - | - | - | - | - | - | - | #REF!
20 |  | Modernization (reconstruction) of 35 kV outdoor switchgear and switchgear-6,10 kV on substations 35\10 kV Teegan, Garmish, Kyzyl-Turan, Ushtagan, Shaiyr, Kazan, Tuschykuduk, Kareernaya (Beyneu) | PCs/cells | 9./12 | - | 2015-2019 |  | 14220 | 14219.8 | - |  | 14219.8 |  |  |  | - | - | - | - | - | - | - | - | - | - | #REF!
21 |  | Replace switchgear-6 kV at the substation 110/6kV "Karazhanbas-2" | PCs/cells | 1./18 | 1./18 | 2015-2016 |  | 27651.449 | 227575.0384 | 199923.5894 |  |  | 227575.0384 |  |  | - | - | - | - | - | - | - | - | - | - | #REF! | На реализацию данного проекта был получен заем от АО "Каражанбасмунай" в размере 200 млн.тенге, оставшаяся часть профинансирована из собственных средств. Реализация проекта завершена.
22 |  | Equipment modernization (reconstruction) of outdoor switchgear 35 kV at substation 35/6kV "Modular cluster pump station-2,3,4,5", Tasbulat, Beket-Ata, Akkuduk, Akjigit | PCs/off | 7./22 | - | 2015-2019 |  | 202139.95 | 201983.37 | -156.58 | According to the results of an open tender and actually concluded contracts. |  | 201983.37 |  |  | - | - | - | - | - | - | - | - | - | - | #REF! | По итогам открытого тендера и фактически заключенным договорам
23 |  | Modernization | [5 empty] | 160247 | 166726.8321 | 6479.8321 |  | 0 | 166726.8321 | 0 |  | - | - | - | - | - | - | - | - | - | - | #REF!
|  | Purchase of production equipment, devices and installations |  |  |  | 2016 |  | 81703.383 | 89074.545 |  | Due to the production necessity, production equipment, devices and installations, current and voltage transformers were purchased |  | 89074.545 |  |  | - | - | - | - | - | - | - | - | - | - | #REF! | В связи с производственной необходимостью приобретены производственное оборудование, приборы и установки, трансформаторы тока и напряжения
|  | Purchase of furniture for industrial premises |  |  |  | 2016 |  | 2732.5 | 1600 |  | According to the results of an open tender and actually concluded contracts. |  | 1600 |  |  | - | - | - | - | - | - | - | - | - | - | #REF! | По итогам открытого тендера и фактически заключенным договорам
|  | Acquisition of technological vehicles |  |  |  | 2016 |  | 9385 | 9385 |  |  |  | 9385 |  |  | - | - | - | - | - | - | - | - | - | - | #REF!
|  | Purchase of household and computer equipment for industrial premises |  |  |  | 2016 |  | 7070.8 | 6687.351 |  | According to the results of an open tender and actually concluded contracts. |  | 6687.351 |  |  | - | - | - | - | - | - | - | - | - | - | #REF! | По итогам открытого тендера и фактически заключенным договорам
|  | Software |  |  |  | 2016 |  | 9912.5 | 14047.559 |  |  |  | 14047.559 |  |  | - | - | - | - | - | - | - | - | - | - | #REF!
|  | Examination services |  |  |  | 2016 |  | 37942.817 | 34432.3771 |  | Rolling project. Deviation from the approved plan, due to the late date of the contract. |  | 34432.3771 |  |  | - | - | - | - | - | - | - | - | - | - | #REF! | Переходящий проект. Отклонение от утвержденного плана, в связи с поздним сроком заключения договора
|  | Engineering services and technical support |  |  |  | 2016 |  | 11500 | 11500 |  |  |  | 11500 |  |  | - | - | - | - | - | - | - | - | - | - | #REF!
|  | TOTAL | [5 empty] | 8936089.3267 | 9490952.1415 | 554863.0147 |  | 1465446.4289 | 1625505.7126 | 6400000 |  | - | - | - | - | - | - | - | - | - | - | #REF!
*- with the approval of the investment programme JSC "MPDC" for the years 2016-2020, the performance of the investment program has not been approved
|  | Chairman of the board of directors | [9 empty] | M. Zhakupov
0
[8 empty] | #REF! |  |  |  | #REF! | #REF! | #REF! | [11 empty] | #REF!
#REF!
[12 empty] | 2471753.2111 | -1006306.7822
[11 empty] | амортиз | 1465446.4289 |  | 1433547.4 | 31899.0289
[11 empty] | капитализ | 711670.9202
[11 empty] | экономия от потерь | 294635.862 |  | 2481661.276 | 3070933 | 589271.724 | 294635.862
0
-294635.862

## Рус за 1 полугодие 2015 год (hidden)
В соответствии с пунктом 7-6 статьи 7 Закона РК от 09.07.1998 года № 272-I "О естественных монополиях и регулируемых рынках"
Информация
субъекта естественной монополии
об исполнении инвестиционной программы (проекта)
АО "МРЭК"
оказывающего услуги по передаче и распределению электроэнергии
за 1 полугодие 2015 года
№ п/п | Наименование показателей инвестиционной программы (проекта) | Кем утверждена (дата, номер приказа) | Годы реализации мероприятий | Сумма инвест. программы, тыс. тенге | Отчет о прибылях и убытках, тыс. тенге* | Информация о плановых и фактических объемах предоставляемых регулируемых услуг (товаров, работ), тыс.кВтч. |  | Источник инвестиций (фактические условие) | Исполнение, фактические параметры (показатели) мероприятия, объекта инвестиционной программы, учтенной в тарифе (ежеквартально, с нарастающим итогом)** |  |  |  |  | Отклонение | Причины отклонения
[6 empty] | План | Факт |  | Количество в натуральном показателе | Сумма инвестиций | источник инвестиций
[11 empty] | Собственные средства (амортизационные отчисления) | Собственные средства (прибыль) | заемные средства (выпуск облигаций)
1 | Крупные стратегические проекты |  |  | 3037386 | 862147 | 1279800 | 1279551 |  |  | 1136311.6843 | 1044931.188 | 91380.4963 | 0 | -1901074.3157
1.1 | Строительство ЛЭП-220кВ Актау-Каражанбас с автотрансформатором 1х125МВА на УРПС "Каражанбас" | Совместный приказ Департамента Комитета по регулированию естественных монополий и защите конкуренции Министерства национальной экономики РК по Мангистауской области от 03 декабря 2014 года №12-ОД и Министерства энергетики РК от 31 декабря 2014 года №244 | 2013-2016 | 896659 |  |  |  | Собственные средства | 1 | 2650 | 2650 |  |  | -894009 | Переходящий проект. Договор заключен. Проект на стадии реализации
1.2. | Строительство ЛЭП-220кВ Актау-Узень с автотрансформаторами 1х250МВА на нефтепромыслах месторождения "Узень" |  | 2014-2015, 2019-2020 | 610700 | [9 empty] | -610700 | Переходящий проект. Договор заключен. Проект на стадии реализации
1.3. | Строительство регионального-диспетчерского центра |  | 2013-2016 | 542027 |  |  |  |  | 1 | 460563.1103 | 460563.1103 |  |  | -81463.8897 | Переходящий проект. Договор заключен. Проект на стадии реализации
1.4. | Реализация проекта по АСКУЭ в сетях 6-10/0,4кВ АО "МРЭК" с внедрением телемеханики и телеизмерений |  | 2013-2016 | 988000 |  |  |  |  | 1 | 653888.3611 | 581718.0777 | 72170.2833 |  | -334111.6389 | Переходящий проект. Договор заключен. Проект на стадии реализации
1.5. | Реконструкция ПС 110/10 кВ "Акшукур" |  | 2013-2015 | [5 empty] | 1 | 19210.2129 |  | 19210.2129 |  | 19210.2129 | Выполнены пусконаладочные работы, авторский и технический надзор
2 | Расширение, модернизация и развитие |  |  | 2241771 | [5 empty] | 45315.727 | 0 | 45315.727 | 0 | -2196455.273
2.1. | Реконструкция ПС ПТФ с переводом напряжения 110кВ и заменой силовых трансформаторов |  | 2015-2018 | 856245 |  |  |  | Собственные средства | [5 empty] | -856245
2.2. | Реконструкция ПС-110/6 кВ ПТБ |  | 2014-2016 | 821100 | [9 empty] | -821100
2.3. | Обслуживание ВЛ-110кВ, ВЛ-220кВ с целью прогнозирования срока службы и повышения грозоупорности ВЛ |  | 2014-2015 | 12326 | [9 empty] | -12326 | Переходящий проект. Договор заключен. Проект на стадии реализации
2.4. | Замена ОД/КЗ-110 кВ на элегазовые выключатели на ПС 110/6 кВ Каражанбас-2 |  | 2013-2015 | [5 empty] | 1 | 728.725 |  | 728.725 |  | 728.725 | Завершение проекта, который был приостановлен актом о приостановке выполнения работ в 2014 году
2.5. | Замена ОД/КЗ-110 кВ на элегазовые выключатели на ПС 110/6 кВ ПТВ |  | 2013-2015 | [5 empty] | 2 | 23485.8868 |  | 23485.8868 |  | 23485.8868 | Завершение проекта, который был приостановлен актом о приостановке выполнения работ в 2014 году
2.6. | Замена ОД/КЗ-110 кВ на элегазовые выключатели на ПС 110/35/10 кВ Форт |  | 2013-2015 | [5 empty] | 2 | 10275.2541 |  | 10275.2541 |  | 10275.2541 | Завершение проекта, который был приостановлен актом о приостановке выполнения работ в 2014 году
2.7. | Замена ОД/КЗ-35кВ на элегазовые выключатели на ПС 35/6 кВ Карьерная |  | 2013-2015 | [5 empty] | 2 | 5234.8611 |  | 5234.8611 |  | 5234.8611 | Завершение проекта, который был приостановлен актом о приостановке выполнения работ в 2014 году
2.8. | Модернизация ячеек КРУН-6 кВ на РП Жетыбай |  | 2014-2015 | 52100 | [9 empty] | -52100 | Планируется объявление тендера
2.9. | Установка SCADA в распределительных сетях с заменой трансформаторов и провода |  | 2013 | 500000 | [9 empty] | -500000
2.10. | Услуги по разработке проекта "Водоснабжение питьевой водой ремонтно-производственной базы" |  | 2014-2015 |  |  |  |  | Собственные средства | 1 | 5591 |  | 5591 |  | 5591 | В связи с необходимостью осуществления водоснабжения объектов АО «МРЭК» в 2014 году были выполнены проектно-изыскательные работы по монтажу системы городского водопровода до РПБ АО «МРЭК». Однако на основании дополнительного соглашения , в связи с длительным сроком получения разрешения от владельцев подземных коммуникаций на производство работ, действие договора было продлено до 31 января 2015 года
3 | Техническое перевооружение |  |  | 0 | [5 empty] | 842.622 | 0 | 842.622 | 0 | 842.622
3.1. | Программное обеспечение |  | 2015 |  |  |  |  | Собственные средства |  | 842.622 |  | 842.622 |  | 842.622 | Приобретены лицензии на обновление программных продуктов
| ИТОГО |  |  | 5279157 | [5 empty] | 1182470.0332 | 1044931.188 | 137538.8452 | 0 | -4096686.9668
|  |  |  | 5279157 | [5 empty] | 1182470.0332 | 1044931.188 | 137538.8452 | 0 | -4096686.9668
-4184686.9668