## Лист1
Appendix 4 to the approved investment policy programs (projects) of the natural monopolies, their adjustments, and analysis of information on their execution
Information of the natural monopoly entity about the course of execution by the entity of the investment program for the 1st half of 2017
JSC "Mangistau power distribution сompany
Information of the natural monopoly entity
Transmission and distribution of electrical energy,
(type of activity)
Approved by the order of DKIM and ZK MNE RK Mangistau region No. 134-OD of November 25, 2016
department of the committee on the regulation of natural monopolies
item number | Information on the implementation of the investment program in the context of funding sources, thousand tenge
| The name of the events | The unit of measurement (for positive indicators) | The quantity in physical indicators |  | The amount of the investment program, thousand tenge |  | own funds |  |  |  | Borrowed funds |  |  |  | Budgetary funds |  | Unregulated (other) activities
|  |  | plan for 2017 | fact for 1 half of the year | plan for 2017 | fact for 1 half of the year | plan for 2017 | fact for 1 half of the year | Deviation | Reasonsfor deviation | plan for 2017 | fact for 1 half of the year | Deviation | Reasonsfor deviation | plan for 2017 | fact for 1 half of the year | plan for 2017 | fact for 1 half of the year
1 | 2 | 3 | 4 | 5 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
1 | Reconstruction of VL-110 kV l-SH-1,2 length 2х131km | km/PCs. | 2x131 |  | 45400 | 0 | 45400 |  |  | The transfer of work on the development of design and estimate documentation from 2017 to 2018 is due to the fact that the project requires for the construction of a new single-line VL-110kV, parallel to the existing one. The construction of this line requires the allocation of land for the installation of supports in the city, which is currently problematic in conjunction with the construction of residential areas, industrial bases, etc. In this regard, during the 2017 evaluation, the development of this project in 2017 is not planned. |  |  |  | There are no deviations, the work is carried out according to the schedule
2 | The construction of transmission lines 110 kV from substation "Uzen"-220kV to substation 110/35/6kV Plateau length (1х18,7 km) with the replacement of transformer 1х40МВА | km/PCs. | 1x18,7 |  | 277392 | 11336.7989 | 77392 | 11336.7989 |  | The contract for the development of plans and estimates have been signed with JSC "KING" in 2017, 11 337 thousand. Currently, plans and estimates have completed the resulting conclusion of state-run enterprise "Gosexpertiza". The contract for construction and installation works has been concluded, to date, organizational work has been performed, construction is planned from the third quarter according to the schedule of work. | 200000
3 | Modernization (reconstruction) of 35 kV outdoor switchgear and switchgear-6,10 kV on substations 35\10 kV Teegan, Garmish, Kyzyl-Turan, Ushtagan, Shaiyr, Kazan, Tuschykuduk, Kareernaya (Beyneu) | PCs/cells | 9./12 |  | 218000 | 0 | 218000 |  |  | The project implementation was postponed from 2017-2018 to 2018-2019. In this regard, during the 2017 evaluation, the development of this project in 2017 is not planned.
4 | Replace switchgear-6 kV at the substation 110/6kV "Karazhanbas-2" | PCs/cells | 1./18 |  | 198200 | 0 | 198200 |  |  | Due to changes in the work schedule
5 | Equipment modernization (reconstruction) of the cells of 110 kV outdoor switchgear at the substation 220/110/10kV "Uzen" No. 1,2,7,8,11,12,15,16,24,25,26,27,28,29,30,31,32 | pris. | 17 |  | 437000 | 68456.313 | 87000 | 68456.313 |  |  | 350000
6 | Modernization (reconstruction) of outdoor switchgear 35, 110 and the RU-6 kV of substation 110/35/6 "Urban" | PCs/off | 1./7 |  | 206000 | 4235 | 206000 | 4235
7 | Equipment modernization (reconstruction) of 110 kV outdoor switchgear and indoor switchgear-6kV S 110/6-6 kV "Industrial zone" | PCs/off | 1./2 |  | 60000 | 0 | 60000
8 | Modernization (reconstruction), equipment of 110 kV outdoor switchgear and switchgear of 10kV of substation 110/10kV "Tyub-Karagan" | PCs/off | 1./11 |  | 78150 | 0 | 78150 |  |  | The project implementation was postponed from 2017-2018 to 2018-2019. In this regard, during the 2017 evaluation, the development of this project in 2017 is not planned.
9 | Modernization (reconstruction) of outdoor switchgear 35 kV and indoor switchgear-6 kV of substation 35/6kV "Pensavo" and 35/6kV substation "East" | PCs/off | 2./41 |  | 230000 | 388112.7304 | 230000 | 388112.7304 |  | The contract for construction and installation work is concluded, according to the schedule, the implementation of the construction and installation is planned from the beginning of the third quarter of 2017.
10 | Equipment modernization (reconstruction) of outdoor switchgear 35 kV at substation 35/6kV "Sauskan" | PCs/off | 1./2 |  | 31000 | 0 | 31000 |  |  | The development of design and estimate documentation has been completed, a positive expert opinion has been obtained, on the basis of this, the approved amount for construction and installation works has increased, the works have been postponed from 2017 to 2018. In this regard, during the evaluation of 2017, the development of this project in 2017 is not planned.
11 | Modernization (reconstruction), equipment of closed switchgear 6 kV at the substation 110/6kV coupling capacitor Uzen with replacement of power transformers 2х10МВА on 2х16МВА and substation of 110/6kV "Tenga" with replacement of power transformers 2x2,5 2х4МВА and modernization of relay protection and automation substation | PCs/transformer/cell. | 2./2/42 |  | 104400 | 0 | 104400 |  |  | The project implementation was postponed from 2017-2018 to 2018-2019. In this regard, during the 2017 evaluation, the development of this project in 2017 is not planned.
12 | Modernization (reconstruction), equipment of indoor switchgear-6 kV substation of 110/6kV "Karamandybas", substation 110/6kV "Thermal" | PCs/cells | 2./39 |  | 330000 | 0 | 130000 |  |  | The contract for construction and installation work is concluded, according to the schedule, the implementation of the construction and installation is planned from the beginning of the third quarter of 2017. | 200000
13 | Modernization (reconstruction) of equipment RU-6, 10kV substation 110/6kV "Support", substation 110/6kV Sai-Utes, substation 110/35/6kV "Dunga", substation 110/10kV "Fort", substation-35/10kV "Kuibyshevo" | PCs. | 5./67 |  | 216855 | 0 | 66855 |  |  | The project implementation was postponed from 2017-2018 to 2018-2019. In this regard, during the 2017 evaluation, the development of this project in 2017 is not planned. | 150000
14 | The replacement of power transformers at substation 110/35/6kV "Zhetybai" capacity 2х40МВА on 2х63МВА | PCs. | 2 |  | 195400 | 0 | 195400 |  |  | With the expansion of the field of oil-producing objects and dynamic population growth in the future will lead to the overloading of the transformer. In order to initiate limiting loads and avoid power shortages transformers 2x40 MBA need to be replaced to 2х63МВА. In this regard, the development of the project is planned in 2017, the implementation of the project is planned in 2018. In this regard, during the evaluation of the year 2017, the development of this project in 2017 is planned in the amount of 31 250 thousand tenge.
15 | The replacement of power transformers at the substation 35/6kV "MGPS-3" with a capacity of 2x6,3МВА on 2х10МВА | PCs. | 2 |  | 117900 | 170331.4506 | 117900 | 170331.4506 |  | According to the daily regime, the load on the power transformers T-1,2 with a capacity of 6,3 MBA during extraction for repair of one of them is equal to 98%. In order to initiate limiting loads and avoid power shortages, works were postponed to 2017. An agreement has been concluded, work is underway on the replacement of transformers.
16 | The replacement of power transformers at the substation 35/6kV "MGPS-3" with a capacity of 2x6,3МВА on 2х10МВА | PCs. | 2 |  | 112500 | 170331.4507 | 112500 | 170331.4507 |  | According to the daily regime, the load on the power transformers T-1,2 with a capacity of 6,3 MBA during extraction for repair of one of them is equal to 98%. In order to initiate limiting loads and avoid power shortages, works were postponed to 2017. An agreement has been concluded, work is underway on the replacement of transformers.
17 | Equipment modernization (reconstruction) of outdoor switchgear 35 kV at substation 35/6kV "Modular cluster pump station-2,3,4,5", Tasbulat, Beket-Ata, Akkuduk, Akjigit | PCs/off | 7./22 |  | 377000 | 505033.3678 | 377000 | 505033.3678 |  | With the development of plans and estimates instead of 35kV gas-insulated switches intended for vacuum reclosers that have a built-in system protection and automation that ensures easy integration into Supervisory control systems, as well as means of dispatching technological control (Supervisory control system) of the substation for data transmission. On the basis of the above, the project was developed by the estimated cost by the above estimates, a conclusion of the examination was obtained. During the evaluation of 2017, the development of this project in 2017 is planned in the amount of 564 658 thousand tenge.
18 | Modernization (reconstruction) of outdoor switchgear 35 kV, indoor switchgear 6 kV substation 35/6 kV "PTF" | PCs/off | 1./17 |  | 31000 | 0 | 31000 |  |  | Construction and installation works on modernization of outdoor switchgear 35 kV and indoor switchgear-6 kV SS-35/6kV substation "PTF" postponed from 2017 to 2018. In this regard, during the evaluation of 2017, the development of this project in 2017 is not planned.
19 | Modernization (reconstruction) of the equipment of indoor switchgear-6-10 kV of substation-35/10/6kV "Tasbulat", "Uchkuduk", "Beket Ata", "Tues", "Tauscan", "Career(Zhetybay)" | PCs/cells | 6./54 |  | 24400 | 0 | 24400 |  |  | Development of design estimates has been postponed from 2017 to 2018, construction and installation works are planned to start in 2018. In this regard, during the 2017 evaluation, the development of this project in 2017 is not planned.
20 | Reconstruction of distribution networks with replacement of packaged transformer substation | km/PCs. | 601/300 |  | 996611.305 | 0 | 396611.305 |  |  |  | 600000
21 | Construction of transmission line-220kV Aktau-Karazhanbas with autotransformer 1x125MBA on management of construction projects Karazhanbas | km/PCs. | 198,6/1 |  |  | 737177.8751 |  | 737177.8751 |  | The increase in the authorized amount of the project 5 719 468 thousand tenge up to 7 047 094 thousand tenge was used for adjustment of the project, which was provided by the increase in transformer capacity of 125 MVA to 150 MVA replace the existing transformers rated for 16 MBA, 25 MBA, replacement obsolete transformers of current and voltage transformers, also considered the suppression of VL-220kV with communications in unintended project. Correction of the project received a positive conclusion RSE № 01-0553/15 from 21.12.2015 year.
22 | The modernization of substation 110/6kV "PTV" with the replacement of indoor switchgear-6 kV for switchgear-6kV | PCs/cells | 1./25 |  |  | 74017.177 |  | 74017.177 |  | The resulting conclusion of RSE "Gosexpertiza" No. 15-0088/16 from 06.04.2016 estimated cost of 286 701 thousand tenge where the setting of modular buildings, combined with the income statement and the complete distribution devices of KRU-6kV replacement of TSN-6kV, replacement bus bridge 6kV. In this regard, during the evaluation of 2017, the development of this project is planned in the amount of 74,017 thousand tenge.
23 | Modernization (reconstruction) of outdoor switchgear 35 kV at substation 110/35/6 " substation "Dent" and substation "Plateau" | PCs/off | 2./10 |  |  | 8330 |  | 8330 |  | Due to the need for additional work, during the evaluation of 2017, the development of this project in 2017 is planned in the amount of 8 330 thousand tenge.
24 | Examination services |  |  |  |  | 11000 |  | 11000
25 | Overhaul and replacement of assets to equivalent ones |  |  |  |  | 3109.445 |  | 3109.445
| TOTAL |  |  |  | 4287208.305 | 2151471.6084 | 2787208.305 | 2151471.6084 | 0 |  | 1500000 | 0 | 0 |  | 0 | 0 | 0 | 0
| Performance, reliability and quality indicators* | fact of the year (half-year) preceding the reporting period | plan (year) | fact of the current year (half-year) | Assessment of performance, reliability and quality indicators | Reasons (justification) for not achieving performance, reliability and quality
Improvement of production indicators, %, by year of implementation depending on the approved investment program (project)
Lowering the depreciation (physical) of fixed assets (assets), %, by years of implementation, depending on the approved investment program (project)
Reduction of losses, %, by years of implementation depending on the approved investment program (project)
Reduction of accidents by year of implementation depending on the approved investment program
* Performance, reliability and quality indicators will be determined at the end of the year.