## Лист1
Appendix 4 to the approved investment policy programs (projects) of the natural monopolies, their adjustments, and analysis of information on their execution
Information of the natural monopoly entity about the course of execution by the entity of the investment program for the 2nd half of 2017
JSC "Mangistau power distribution сompany
Information of the natural monopoly entity
Transmission and distribution of electrical energy,
(type of activity)
Approved by the order of DKIM and ZK MNE RK Mangistau region No. 84-OD of November 29, 2017
department of the committee on regulation of natural monopolies
item number | Information on the implementation of the investment program in the context of funding sources, thousand tenge
| The name of the events | The unit of measurement (for positive indicators) | The quantity in physical indicators |  | The amount of the investment program, thousand tenge |  | own funds |  |  |  | Borrowed funds |  |  |  | Budgetary funds |  | Unregulated (other) activities
|  |  | plan for 2017 | fact for 2nd half of the year | plan for 2017 | fact for 2nd half of the year | plan for 2017 | fact for 2nd half of the year | Deviation | Reasons for deviation | plan for 2017 | fact for 2nd half of the year | Deviation | Reasonsfor deviation | plan for 2017 | fact for 2nd half of the year | plan for 2017 | fact for 2nd half of the year
1 | 2 | 3 | 4 | 5 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
1 | Construction of transmission line-220kV Aktau-Karazhanbas with autotransformer 1x125MBA on management of construction projects "Karazhanbas" | km/PCs. | 198,6/1 | 147/1 | 1325688.7518 | 1291192.2143 | 1156854.9108 | 1291192.2143 | -134337.3035 | The increase in the authorized amount of the project was used for adjustments to increase transformer capacity of 125 MVA to 150 MVA, replace the existing transformers rated for 16 MBA, 25 MBA, replacement obsolete transformers of current and voltage transformers, also considered the suppression of VL-220kV with communications in unintended project. Correction of the project received a positive conclusion RSE № 01-0553/15 from 21.12.2015 year. ЭСAlso in 2017, during the expansion of outdoor switchgear-220 kV thermal power plant-3 LLP "Mangistau nuclear power plant - Kazatomprom" has additionally required to provide landscaping and the device paths of the order, on the upper edge of the fence, canopy sheild wire "Egoza", antiundermining fence. As for the expansion of the outdoor switchgear-220kV, the project did not provide for the installation of an oil collector, installation of cable trays, filling the site with crushed stone. | 168833.841 | 0 | 168833.841 | There are no deviations, the work is carried out according to the schedule
2 | Modernization (reconstruction) of outdoor switchgear 35 kV at substation 110/35/6 "Plateau", substation110/35/6 "Dent" | PCs/off | 2./10 | 2./10 | 8330 | 30825.1981 | 8330 | 30825.1981 | -22495.1981 | In the absence in the working draft of the communication circuits of relay protection and automation of the existing equipment with newly installed equipment of outdoor switchgear 35 kV reclosers along with card settings were carried out work on the integration of existing equipment as part of the RPA at currently the work is performed.
3 | Reconstruction of outdoor switchgear 35 kV,110 kV with the replacement of the OD/short circuit-110 kV and 35 kV installation of reclosers at the substation 110/35/6kV "East Zhetybay" | PCs/off | 1./9 | 1./9 | 4900 | 4900 | 4900 | 4900 | 0 | Installation and design waste generation standards - disposal limits, completed The new equipment was put into operation.
4 | Modernization of the RU-6 kV at the substation 110/6kV "PTV" with the replacement of indoor switchgear-6 kV for switchgear-6kV | PCs/cells | 1./25 | 1./25 | 74017.177 | 0 | 19276.828 | 0 | 19276.828 | Design and estimate documentation was generated by "KING" limited company and the resulting conclusion by RSE "Gosexpertiza" No. 15-0088/16 from 06.04.2016 estimated cost of 286 701 thousand tenge where the setting of modular buildings, combined with the income statement and the complete distribution devices of KRU-6kV replacement of TSN-6kV, replacement bus bridge 6kV. Construction and installation work started in 2016, the remaining part of the work was moved to 2017. works are completed. | 54740.349 | 0 | 54740.349
5 | The construction of transmission lines 110 kV from substation "Uzen"-220kV to substation 110/35/6kV Plateau length (1х18,7 km) with the replacement of transformer 1х40МВА | km/PCs. | 1x18,7 | 1 | 523513.8589 | 520680.128 | 371413.8589 | 368580.128 | 2833.7309 | Design and estimate is completed, the resulting conclusion by RSE "Gosexpertiza" No. 15-0016/17 as of 20.01.2017, estimated costs more than planned. Work is underway to implement this project. Completion is scheduled for 2018. | 152100 | 152100 | 0
6 | Equipment modernization (reconstruction) of the cells of 110 kV outdoor switchgear at the substation 220/110/10kV "Uzen" No. 1,2,7,8,11,12,15,16,24,25,26,27,28,29,30,31,32 | pris. | 17 | 7 | 200846.3469 | 161386.487 | 200846.3469 | 161386.487 | 39459.8599 | Currently, the design and estimate documentation is completed with an estimated cost greater than the pledged one. The resulting conclusion of RSE Gosexpertiza No. 15-0093/16 from 11.04.2016 year.This project is planned to be completed in 2018.
7 | Modernization (reconstruction) of equipment ORU-110 PS 110/35/6kV "Gorodskaya" | PCs/off | 1./2 | 1./2 | 44311.1005 | 40076.0604 | 44311.1005 | 40076.0604 | 4235.0401 | Design estimates for modernization of the equipment of 110 kV outdoor switchgear is designed, received a report of RSE Gosexpertiza No. 15-0089/16 from 06.04.2016 year. Construction and installation work began in 2016 by "ABC-Kurylys" LLP, part of the work was completed, the remaining part of the work was postponed to 2017. Estimates for the modernization of indoor switchgear-6kV developed, obtained expert opinion No. FE-0097/16 from 07.11.2016 G.
8 | Modernization (reconstruction), equipment of 110 kV outdoor switchgear of 110/6-6 kV "PromZona" | PCs/off | 1./2 | 1./2 | 32224.0285 | 32224.0285 | 32224.0285 | 32224.0285 | 0 | Installation and design waste generation standards - disposal limits, completed The new equipment was put into operation.
9 | Modernization (reconstruction), equipment of indoor switchgear-6 kV of substation 35/6kV "Glinzavod" and substation -35/6kV "Vostochnaya". | PCs/off | 2./41 | 2./41 | 513020.138 | 131793.8977 | 240978.838 | 131793.8977 | 109184.9403 | Design estimates completed, positive conclusion of the examination No. FE-0096/16 dated 07.11.2016. And № FE-0093/16 from 07.11.2016, the cost is higher than planned due to the fact that the project provided for transformer protection panels and own needs. Currently, the project is being implemented by "Smart engineering Group"LLP. Completion is scheduled for 2017. | 272041.3 | 0 | 272041.3
10 | Modernization (reconstruction), equipment of indoor switchgear-6 kV substation of 110/6kV "Karamandybas", substation 110/6kV "Thermal" and modernization of relay protection and automation substation | PCs/cells | 2./39 | 2./39 | 499686.841 | 526944.8423 | 279101.461 | 306359.461 | -27258 | Design estimates completed, positive conclusion of the examination No. FE-0095/16 dated 07.11.2016. And № FE-0094/16 from 07.11.2016, the cost is higher than planned due to the fact that the project provided for transformer protection panels and own needs. Currently, the project is being implemented by "Smart engineering Group" LLP completion is planned this year. | 220585.38 | 220585.3813 | -0.0012843
11 | The replacement of power transformers at substation 110/35/6kV "Zhetybai" capacity 2х40МВА on 2х63МВА | PCs. | 2 | - | 32967.492 | 0 | 32967.492 | 0 | 32967.492 | Development of design estimates was canceled due to the lack of need to replace transformers, as there is no increase in additional loads by analyzing the code of issue of technical conditions and infrastructure development of Zhetybay as a whole
12 | The replacement of power transformers at the substation 35/6kV "MGPS-3" with a capacity of 2x6,3МВА on 2х10МВА | PCs. | 2 | 2 | 177556.663 | 7706.2274 | 29546.641 | 7706.2274 | 21840.4136 | Design estimates developed, the estimated cost of the work was less than planned.The project is completed. | 148010.022 | 0 | 148010.022
13 | The replacement of power transformers at the substation 35/6kV "MGPS-3" with a capacity of 2x6,3МВА on 2х10МВА | PCs. | 2 | 2 | 177556.663 | 7706.2274 | 29546.641 | 7706.2274 | 21840.4136 | Design estimates developed, the estimated cost of the work was less than planned. The project is completed | 148010.022 | 0 | 148010.022
14 | Equipment modernization (reconstruction) of outdoor switchgear 35 kV at substation 35/6kV "Modular cluster pump station-2,3,4,5", Tasbulat, Beket-Ata, Akkuduk, Akjigit | PCs/off | 7./22 | 7./22 | 549208.84 | 47115.9025 | 213529.898 | 47115.9025 | 166413.9955 | With the development of plans instead of 35kV gas-insulated switches intended for vacuum reclosers that have a built-in system protection and automation that ensures easy integration into Supervisory control systems, as well as means of dispatching technological control (Supervisory control system) of the substation for data transmission. On the basis of the above, the project was developed by the estimated cost by the above estimates, a conclusion of the examination was obtained. This year 4 substation -35/6kV "MGPS-3", "MGPS-4""MGPS-5", "Tasbulat", have been upgraded, the work was completed. The remaining substation are planned to be implemented in 2018. | 335678.942 | 0 | 335678.942
15 | Modernization (reconstruction) of outdoor switchgear 35 kV, indoor switchgear 6 kV substation 35/6 kV "PTF" | PCs/off | 1./17 | - | 24703.0214 | 19762.4171 | 24703.0214 | 19762.4171 | 4940.6043 | The DED was developed by 90%, but the completion was postponed to 2018, as to obtain the conclusion of the state expertise, the project support by the designer is required and the consideration takes 45 working days, which is not possible until the end of 2017.
16 | Modernization (reconstruction) of 35 kV outdoor switchgear and switchgear-6,10 kV on substations 35\10 kV Teegan, Garmish, Kyzyl-Turan, Ushtagan, Shaiyr, Kazan, Tuschykuduk, Kareernaya (Beyneu) | PCs/cells | 9./12 | 9./12 | 11000 | 0 | 11000 | 0 | 11000 | Development of design estimates completed.
17 | Acquisition of main equity and intangible assets |  |  |  | 87677.078 | 110981.919 | 87677.078 | 110981.919 | -23304.841 | In conjunction with the production need, power and current transformers, devices and equipment, as well as technological vehicles were purchased
| TOTAL |  |  |  | 4287208 | 2933295.5495 | 2787208.144 | 2560610.1682 | 226597.9758 |  | 1499999.856 | 372685.3813 | 1127314.4747 |  | 0 | 0 | 0 | 0
| Performance, reliability and quality indicators* | fact of the year (half-year) preceding the reporting period | plan (year) | fact of the current year (half-year) | Assessment of performance, reliability and quality indicators | Reasons (justification) for not achieving performance, reliability and quality
Improvement of production indicators, %, by year of implementation depending on the approved investment program (project)
Lowering the depreciation (physical) of fixed assets (assets), %, by years of implementation, depending on the approved investment program (project)
Reduction of losses, %, by years of implementation depending on the approved investment program (project)
Reduction of accidents by year of implementation depending on the approved investment program
* Performance, reliability and quality indicators will be determined at the end of the year.